## Sheet1
|  |  | Ideal Story Points to complete | Actual Story Points to complete | Planned completion Story points | Actual completion Story Points
|  | Total | 84 | 84
Release 1 | Iteration 1 | Week 6 | 76 | 81 | 8 | 3
|  | Week 7 | 66 | 73 | 10 | 8
| Iteration 2 | Week 8 | 55 | 61 | 11 | 12
|  | Week 9 | 46 | 47 | 9 | 14
| Break |  | 46 | 45
Release 2 | Iteration 3 | Week 10 | 35 | 39 | 11 | 8
|  | Week 11 | 22 | 27 | 13 | 12
| Iteration 4 | Week 12 | 12 | 15 | 10 | 12
|  | Week 13 | 0 | 0 | 12 | 15
Ideal
Actual