## Sheet1
Task | Date Assigned | Description | Assigned To | Status | Completed by | Estimated Time | Actual Time
iteration 2
i2-x | 2012-09-11 | Use Selenium to implement user acceptance tests | Courtney and Nicholas | Complete | Courtney and Nicholas | 3 hours
i2-x | 2012-09-11 | Improve appearance UI | Sen and Aaron | Complete | Sen and Aaron
i2-x | 2012-09-11 | More Junit tests | Sen | Complete | Sen
i2-x | 2012-09-11 | Burndown charts | Courtney | Complete | Courtney
i2-x | 2012-09-11 | Progress reports | Sen | Complete | Sen
i2-8 | 2012-09-11 | Research to gather feed-in tariffs in different states and store the Data in Google data store | Sen | Postponed
i2-9 | 2012-09-11 | Design a class that calculates energy generated based on given values (average sunlight per day and Australian state) | Sen | Complete | Sen
i2-10 | 2012-09-11 | Implement the ability to calculate energy generation with minimal user input. | Sen and Aaron | Complete | Sen and Aaron
i2-11 | 2012-09-11 | Research and implement different brands of solar panels for the user to choose from | Nicholas | Complete | Sen
i2-12 | 2012-09-11 | Implement the above changes into the solar generation | Aaron | Postponed
i2-13 | 2012-09-11 | Research and develop a formula to calculate savings | Sen and Felix | Complete | Sen
i2-14 | 2012-09-11 | Code the formula and implement a method to display results | Sen and Aaron | Complete | Sen and Aaron
i2-15 | 2012-09-11 | Research and enable the ability to implement graphs into the client | Aaron | Postponed
i2-16 | 2012-09-11 | Implement methods to create and display a chart using ROI as the data | Aaron | Postponed
i2-x | 2012-09-11 | Update Story Cards | Courtney | Complete | Courtney
i2-x | 2012-09-11 | Updates Iteration Plan | Courtney | Complete | Courtney
i2-8 | 2012-09-18 | Research to gather feed-in tariffs in different states and store the Data in Google data store | Nicholas and Courtney | Postponed
i2-11 | 2012-09-18 | Research and implement different brands of solar panels for the user to choose from | Sen | Complete | Sen
i2-12 | 2012-09-18 | Implement the above changes into the solar generation (autopopulate textboxes) | Felix | Complete | Sen
i2-15 | 2012-09-18 | Research and enable the ability to implement graphs into the client | Aaron | Complete | Sen
i2-16 | 2012-09-18 | Implement methods to create and display a chart using ROI as the data | Aaron | Complete | Sen
iteration 3 (part1)
i3-1 | 2012-09-18 | Implement the ability to select user's location (city) | Sen | Complete | Sen
i3-5 | 2012-09-18 | Gather solar irradiance values for all cities in Australia | Felix | Complete | Sen and Felix
i3-2 | 2012-09-18 | Integrate user's location into the calculation of power generated | Sen | Complete | Sen
i3-3 | 2012-09-18 | Display results in a clear and concise summary | Sen | Postponed
i3-4 | 2012-09-18 | Implement a message stating how much the user saves (or stands to lose). | Courtney | Complete | Courtney | 6 hours | 6 hours
i3-6 | 2012-09-18 | Setup a database with location information | Nicholas and Courtney | Complete | Sen | 6 hours | 10 hours
i3-7 | 2012-09-18 | Enable the server to communicate with the database | Nicholas and Courtney | Complete | Sen | 6 hours | 6 hours
|  | desktop app UI design | Aaron | Complete | Aaron
iteration 3 (part2)
| 2012-10-02 | add more cities and postcode | Sen | Complete | Sen | 2 hours | 3 hours
| 2012-10-02 | update database (add more tables and data) | Sen | Complete | Sen | 3 hours | 4 hours
| 2012-10-02 | auto detect city | Sen | Complete | Sen | 3 hours | 3 hours
| 2012-10-02 | initial code refactoring | Sen | Complete | Sen | 2 hours | 3 hours
| 2012-10-02 | improve UI layout | Sen | Complete | Sen | 3 hours | 5 hours
| 2012-10-02 | continue with desktop app | Aaron | Complete | Aaron
| 2012-10-02 | similar system generation in web app (optional) | Courtney | Complete | Sen
| 2012-10-02 | selenium tests and user acceptance tests | Nick | Complete | Nick
| 2012-10-02 | More junit tests ( for CityDAO class, CalculationFormulas class) | Nick | Complete | Sen
| 2012-10-02 | more code refactoring | Courtney | Complete | Courtney | 1 hour
| 2012-10-02 | keep up documentation and reports burndown charts etc | Courtney | Complete | Courtney | - | -
iteration 4(part1)
|  | implement subsidy feature | Sen | Complete | Sen | 1 hour | 1 hour
|  | revise user stories and iteration plans | Sen | Complete | Sen | 3 hours | 3 hours
|  | angles and roof directions | Sen | Complete | Sen | 3 hours | 4 hours
|  | get desktop demo ready | Aaron | Complete | Aaron | 5 hours | 6 hours
|  | More junit tests (CalculationFormulas class) | Court | Complete | Court | 4 hours | 4 hours
|  | prepare powerpoint for presentation | Court | Complete | Court | 1 hour | 1hour
|  | selenium tests and user acceptance tests | Nick | Complete | Nick | 1 hour | 1hour
|  | implement validate user input function | Nick | Complete | Nick | 2 hours | 2 hours
|  | Retrieve solar products from database and display them on the web app | Felix | Postponed
Iteration 4(part2)
|  | implement multiple clusters selection | Sen | Complete | Sen | 2 hours | 2 hours
|  | implement optimal degrees based on user location | Court | Complete | Court | 2 hours | 1 hour
|  | implement return on investment for solar panels and high interest bank account | Court | Complete | Court | 1 hour | 1hour
|  | improve validation feature | Nick | Complete | Nick | 2 hours | 2 hours
|  | selenium tests | Nick | Complete | Nick | 2 hours | 2 hours
|  | desktop | Aaron | Complete | Aaron | 7 hours | 6 hours
|  | Retrieve solar products from database and display them on the web app | Felix | Complete | Felix | 4 hours | 5hours
Note on E1: Let us know how your tasks go, do you need help? can you finish it on time? etc