## Sheet1
Please spend at least 10 hours on the project each week or longer to get tasks done.Please take initiatives to help others or do something to improve our project
Task | Description | Date Assigned | Assigned To | To check by | Completion criteria | Status | Estimated Time | Actual Time
i2-x | Use Selenium to implement user acceptance tests | 2012-09-11 | Courtney and Nicholas | Aaron | tests done | Complete | 3 hours
i2-x | Improve appearance UI | 2012-09-11 | Sen and Aaron | Felix | UI looks improved charts and reports to be completed | Complete
i2-x | More Junit tests | 2012-09-11 | Sen | Felix | More tests to be added | Complete
i2-x | Burndown charts | 2012-09-11 | Courtney | Felix | charts to be completed | Complete
i2-x | Progress reports | 2012-09-11 | Sen | Felix | reports to be completed | Complete
i2-8 | Research to gather feed-in tariffs in different states and store the Data in Google data store | 2012-09-11 | Sen | Aaron |  | Postponed
i2-9 | Design a class that calculates energy generated based on given values (average sunlight per day and Australian state) | 2012-09-11 | Sen | Felix |  | Complete
i2-10 | Implement the ability to calculate energy generation with minimal user input. | 2012-09-11 | Sen and Aaron | Courtney |  | Complete
i2-11 | Research and implement different brands of solar panels for the user to choose from | 2012-09-11 | Nicholas | Felix |  | Postponed
i2-12 | Implement the above changes into the solar generation | 2012-09-11 | Aaron | Sen |  | Postponed
i2-13 | Research and develop a formula to calculate savings | 2012-09-11 | Sen and Felix | Nicholas |  | Complete
i2-14 | Code the formula and implement a method to display results | 2012-09-11 | Sen and Aaron | Nicholas |  | Complete
i2-15 | Research and enable the ability to implement graphs into the client | 2012-09-11 | Aaron | Sen |  | Postponed
i2-16 | Implement methods to create and display a chart using ROI as the data | 2012-09-11 | Aaron | Courtney |  | Postponed
i2-x | Update Story Cards | 2012-09-11 | Courtney | All |  | Complete
i2-x | Updates Iteration Plan | 2012-09-11 | Courtney | All |  | Complete
i2-8 | Research to gather feed-in tariffs in different states and store the Data in Google data store | 2012-09-18 | Nicholas and Courtney | Aaron |  | Incomplete
i2-11 | Research and implement different brands of solar panels for the user to choose from | 2012-09-18 | Sen | Felix |  | Incomplete
i2-12 | Implement the above changes into the solar generation (autopopulate textboxes) | 2012-09-18 | Felix | Sen |  | Incomplete
i2-15 | Research and enable the ability to implement graphs into the client | 2012-09-18 | Aaron | Sen |  | Incomplete
i2-16 | Implement methods to create and display a chart using ROI as the data | 2012-09-18 | Aaron | Courtney |  | Incomplete
i3-1 | Implement the ability to select user's location (city) | 2012-09-18 | Sen | Aaron |  | Incomplete
i3-5 | Gather solar irradiance values for all cities in Australia | 2012-09-18 | Felix | Sen |  | Incomplete
i3-2 | Integrate user's location into the calculation of power generated | 2012-09-18 | Sen | Courtney |  | Incomplete
i3-3 | Display results in a clear and concise summary | 2012-09-18 | Sen | All |  | Incomplete
i3-4 | Implement a message stating how much the user saves (or stands to lose). | 2012-09-18 | Courtney |  |  | Complete | 6 hours | 6 hours
i3-6 | Setup a database with location information | 2012-09-18 | Nicholas and Courtney |  |  | Incomplete | 4 hours
i3-7 | Enable the server to communicate with the database | 2012-09-18 | Nicholas and Courtney |  |  | Incomplete | 6 hours | 10+
i4-8 | Create inputs for the user to use
i4-9 | Implement the preset data to the inputs
i4-10 | Display calculations in a readable format
i4-11 | Write a disclaimer that is clearly visible on the website client
Note on E3: The rule for deciding checkers is always check the work of the person right below you.The bottom person check top person
Note on G3: Let us know how your tasks go, do you need help? can you finish it on time? etc